## Sheet1
AGRIFLASK · Sprint Retrospective
US2 – Crop Recommendation & Role-Based Prediction
| What Went Well | What Went Poorly | What Ideas Do You Have | How Should We Take Action
Guidelines | Highlights successes and positive outcomes from the sprint. | Identifies challenges, roadblocks, or failures encountered. | Brainstorms new approaches and strategies for improvement. | Outlines specific steps to address issues in the next sprint.
Point 1 | The core crop recommendation model was successfully integrated across all three user modes. Farmer, Analyst, and Student modes each received correct predictions from the trained Random Forest classifier. The qualitative-to-numeric mapping pipeline for Farmer mode returned agronomically consistent numeric features during system testing. | The initial qualitative-to-numeric mapping for Farmer mode had inconsistent range boundaries for soil fertility and humidity levels, which caused some incorrect predictions during early testing rounds. Additional iteration was required to align the mapping logic with the model's training distribution. | Define and lock the numeric mapping ranges for all qualitative Farmer inputs before development starts. Create a validated mapping lookup table cross-referenced against the model's training data distribution to prevent boundary mismatches. | For all future feature engineering tasks, prepare a mapping specification document during the design phase. Include unit tests for the qualitative-to-numeric conversion layer and run them independently before integrating with the main prediction pipeline.
Point 2 | Multi-level input validation was implemented successfully across all user modes, covering required field checks, hard boundary enforcement, and realistic soft-limit warnings. Domain-consistency checks correctly flagged unrealistic environmental combinations such as low rainfall paired with high humidity, providing clear and actionable feedback to users. | Soft-limit warnings were inconsistently applied between Farmer and Analyst modes during initial development. Several known-unrealistic soil-weather combinations did not trigger domain-consistency warnings as expected, which required additional debugging effort and delayed sprint completion. | Develop a centralized validation rule registry shared across all user modes to ensure consistent validation behavior. Include integration tests specifically for boundary conditions and known domain-inconsistent input combinations to catch regressions early. | Refactor all input validation logic into a single shared validation module used by every user mode route. Write parametrized test cases for all boundary values and unrealistic environmental combinations. Validate these tests pass before marking any prediction-related task as done.
Point 3 | The three role-based UI templates were completed with correct routing and session-based role redirection. Analyst mode's enriched output panel, including confidence labeling, alternative crop suggestions, feature importance display, and radar-style profile comparison, worked correctly and matched the intended design specification. | The Student mode explanatory output was initially too technical in language and detail, not matching the intended simplified, learning-focused persona. Multiple rework cycles were required to reduce complexity and make reasoning output accessible to non-specialist users. | Define output language style, explanation depth, and terminology guidelines for each user persona before frontend development begins, similar to a content design specification. Ensure all three personas have clearly differentiated output requirements documented. | Create a persona-output specification document listing the expected explanation complexity, terminology level, and visible fields for each role. Require sign-off on UI copy against this specification before marking frontend tasks as complete in the sprint backlog.
Point 4 | Multilingual support for English, Hindi, and Tamil was implemented using backend translation dictionaries and a language selection flow. Session persistence for language preference worked correctly, allowing users to switch languages mid-session without losing their prediction inputs or authentication state. | Tamil translations were found to be incomplete and inconsistently applied across several UI templates during integration testing. Some labels and error messages defaulted to English in Tamil mode, requiring rework after the initial integration review, which added unplanned effort to the sprint. | Build a translation completeness validator that checks all dictionary keys are present and non-empty for every supported language before a build is released. Integrate this check into the development pipeline as a mandatory pre-deployment step. | Add a translation validation step to the sprint definition of done checklist. Assign dedicated language reviewers for Tamil and Hindi content and require their sign-off before sprint closure. Log any incomplete translations as bugs in the backlog immediately upon discovery.